{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["RK-02-2002-17,  př. 1a"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"RK-02-2002-17,  př. 1a","index":0,"n_rows":11,"n_cols":14,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,12,0,13],[0,5,0,7],[0,8,0,9],[0,10,0,11]],"flags":["formulas_cached_only"]}
["ISPROFIN","třída","Název akce","Okres","MM/RR","náklady",null,null,2001,null,2002,null,2003]
[{"$nulls":5},"celkem","IV","NIV","IV","NIV","IV","NIV","IV","NIV"]
[3271300000,"II","II/360 Oslavička - sesuv","TR","01/02-12/02",13000,13000,0,0,0,13000,0,0,0]
[3271300000,"II","II/360 Velké Meziřičí - obchvat","ZR","01/02-12/02",110000,110000,0,0,0,15000,0,0,0]
[3271300000,"II","II/360 Třebíč-Velké Meziříčí zkapacitnění kom. příprava","TR/ZR","01/02-12/02",20000,20000,0,0,0,20000,0,0,0]
[3271300000,"II","II/602 Velké Meziříčí -most","ZR","01/02-12/02",6000,6000,0,0,0,6000,0,0,0]
[3271306300,"IIaIII","Příprava a zabezpečení staveb II.a III.tř.kr.Vysočina",null,"01/02-12/02",2212,2212,0,0,0,2212,0,0,0]
[3271326282,"II","II/360 Oslavička - Třebíč, okr. TR","TR","01/02-12/02",10300,10300,0,10200,0,100,0,0,0]
[3271326283,"II","II/353 Nové Veselí-Bohdalov I, okr. ZnS (nákl.dle SFDI)","ZR","01/02-12/02",39587,39587,0,5500,0,18687,0,400,0]
[3271400000,"III","III/36062 mosty Třebíč","TR","01/02-12/02",9000,9000,0,0,0,9000,0,0,0]
[null,null,"celkem",null,null,210099,210099,0,15700,0,83999,0,400,0]